## 07-13th Sep 2015
Module | Function | Coding | Dev Status | Production Status | Comments
User | Creation | Done | Done | Done | Mail Sent to User's Registered Email ID | 2015-09-13
| On Createion, Mail to refered by other than customer | Done | Done |  | Mail Sent to User's Registered Email ID | 2015-09-13
| Updation | Done | Done | Done | Mail Sent to User's Registered Email ID | 2015-09-13
| Deletion | Done | Done |  | Mail Sent to User's Registered Email ID | 2015-09-13
User adding confirmation and activation mail.
Contractor | Create | Done | Done |  | Mail Sent to Official Email ID | 2015-09-13
| Update | Done | Done |  | Mail Sent to Official Email ID | 2015-09-13
Deletion
Contractor adding confirmation and activation mail.
Partner | Create | Done | Done |  | Mail Sent to Official Email ID | 2015-09-13
| Update | Done | Done |  | Mail Sent to Official Email ID | 2015-09-13
Deletion
Contractor adding confirmation and activation mail.
Project | Create - Customer | Done | Done |  | Create Project mail will be sent to the customer Selected, Mail will be sent to registered mail ID | 2015-09-13
| Create - Contractors | Done | Done |  | Create Project mail will be sent to the selected contractors in the project. Mail sent to official mail id of contractor | 2015-09-13
| Create - Adjusters | Done | Done |  | Create Project mail will be sent to the selected adjuster in the project. Mail sent to official mail id of adjuster | 2015-09-13
| Update - Customer | Done | Done |  | Same as create project | 2015-09-13
| Update - Contractors | Done | Done |  | Same as create project | 2015-09-13
| Update - Adjusters | Done | Done |  | Same as create project | 2015-09-13
| Deletion | Done | Done |  |  | 2015-09-21
Task | Create | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
| Update | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
| Deletion | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
Project > Issues | Create | Done | Done |  | Mail sent to customer and all the stack holders | 2015-09-21
| Update | Done | Done |  | Mail sent to customer and all the stack holders | 2015-09-21
| Cancel / Close | Done | Done |  | Mail sent to customer and all the stack holders | 2015-09-21
Task > Issues | Create | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
| Update | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
| Cancel / Close | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
Project > Notes | Create | Done | Done |  | Mail sent to customer and all the stack holders | 2015-09-21
| Deletion | Done | Done |  | Mail sent to customer and all the stack holders | 2015-09-21
Task > Notes | Create | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
| Deletion | Done | Done |  | Mail sent to customer and the project owner | 2015-09-21
Project > Document | Create | Done | Done |  | Mail sent to customer and all the stack holders | 2015-09-21
| Deletion | Done | Done |  | Mail sent to customer and all the stack holders | 2015-09-21
| Issue is not displayed after add and update | Done |  |  |  | 2015-09-21
| Task Not displayed adjuster | Done |  |  |  | 2015-09-21
| Mouse hover help text is added for project list buttons | Done |  |  |  | 2015-09-21
| Mouse hover help text is added for contractors list buttons | Done |  |  |  | 2015-09-21
| Mouse hover help text is added for issues list buttons | Done |  |  |  | 2015-09-21
| Mouse hover help text is added for partner list buttons | Done |  |  |  | 2015-09-21
| Mouse hover help text is added for task list buttons | Done |  |  |  | 2015-09-21
| All the tabs need to move the right side of interface | Done |  |  |  | 2015-09-21
| Task list page, tabs need to move to the right | Done |  |  |  | 2015-09-21
| Task list page, the column names - Tasks and Descriptions should have be on the left margin of the column | Done |  |  |  | 2015-09-21
Project List page, 'Project Name' needs to be moved over the projects in the column
| Project List page title should be changed to 'List of Projects' | Done |  |  |  | 2015-09-21